## Slide 1: Websense’s Agile Journey
Ami Kleinman
Senior Director, Software Engineering

## Slide 2: Agenda
How We Got to Agile?
Gearing up for Agile Scrum
Kicking off Agile Scrum
Assessment of Agile

## Slide 3
Before Agile:
“…וְהָאָרֶץ, הָיְתָה תֹהוּ וָבֹהוּ, וְחֹשֶׁךְ, עַל-פְּנֵי תְהוֹם”
בראשית א, ב

## Slide 4: How We Got to Agile
Well … actually not
  Happy with our waterfall process
New VP decided on move to Agile
  Had previous success with Agile
  Main driver was improving quality
Local team started thinking about Agile independently
  Liked tight Dev/QA interaction
  Liked the emphasis on organic cross-functional teams

## Slide 5: Key Decisions
Key Decisions When Moving to Agile:
Pilot with one scrum or all-in ???
  Went all-in
Forming Scrums
  Mostly organic scrums with dedicated QA
    i.e. Engine, GUI, etc.
    Dramatic impact on QA org
  One scrum vertically integrated
  Small infrastructure scrums (CM, Installer, UX)
Identifying Scrum Masters
  Made Team Leaders the SM’s
    Minimize amount of change we introduced
    Not all TL’s were pro-Agile . . .
  This changed over time, but many TL’s still SM’s

## Slide 6: Key Decisions (Con’t)
Identifying Product Owners
  Used senior development managers
Size of Scrums
  Started on the large side (closer to 9 per scrum)
  Over time tried to tweak down
  Too small is a problem also
Scrum of Scrums
Sprint duration
  Used 3 weeks
Hardening Sprint
  Initially 2 hardening sprints in 4-sprint PSI (ouch!!)

## Slide 7: Putting the pieces into place
Gearing up for first sprint requires effort
  Agile training (SM’s and non-SM’s)
  Tools training (Jira in our case)
  Creating Epics/User Stories/Backlogs
  First sprint pre-planning
  Props (sticky cards, clocks, white board,…)

## Slide 8: External Consultant
External Agile consultant was critical for us
Gave us courage to take big decisions!!!
  Sanity checked our ideas
  Allowed us to move more quickly
    Less need to move incrementally
Helped prep for first sprint
Real-time support in early scrum meetings/rituals
  reduced the emphasis on Agile mechanics
  Helped coach the teams (e.g. how to do a good retro)
  Perceived as neutral during disagreements
  Can give more help to scrums that are struggling

## Slide 9: Kicking off Agile
Senior manager involvement and support is critical
  Team needs to see management is fully engaged
Focus on quick adjustments at first
  Try to get to demo and retrospective quickly
  Agile Steering Committee
  Scrum Master Forum
  Track indicators (burn-down)
Expect complaints about process
  Too many meetings
  The meetings take too long (planning, daily, etc.)
  Jira is a hassle
  Burn-down is meaningless
  Etc. etc. etc.

## Slide 10
Assessing Agile at Websense Raanana

## Slide 11: The Good
Excellent cooperation btw Dev and QA
  Dev understands QA better
  QA understand Dev better
  Dev willing to help with QA when needed
QA Team loves SCRUM, feels empowered
  Involved from day one!
  Dev much more open to QA concerns
Quality
  The code doesn’t become unstable
  Mindset -- think a lot more about test cases, unit/regression testing earlier
  Huge emphasis on automation pays dividends

## Slide 12: The Good (con’t)
Forces ruthless prioritization. Frequently.
  Every PSI (quarterly)
  Every Sprint (tri-weekly)
  Emphasis on taking stuff out (for convergence)
Improved Customer Support
  Now owned by the SCRUM (i.e. both Dev and QA)
We improve over time
  Better at executing the rituals
    shorter dailies, effective retrospectives, etc.
  Better at allocating time for pre-planning and PSI planning
  Continually improving our processes
    Post retrospectives, Agile steering, Hardening in the scrum
  More automation

## Slide 13: The Bad
The quality of the SM’s is crucial for success
  Need right people in SM role
  Need critical mass of “pro-agile” scrum members
  Need SM with a sense of ownership
  Project management skills help
De-emphasizes Designs
Many months for teams to acclimate
  Stop complaining about meetings
  Living with Jira/log work/burn-down
  Allocating time for pre-planning/story time
  Effective SoS meetings

## Slide 14: The Bad (con’t)
Keeping Jira up-to-date is a lot of effort
  The engineers don’t update enough (log work)
  Requires constant management attention
    Creating tickets for everything
    Filling out all the key fields
    Etc.
Field support doesn’t fit neatly into Agile
  We allocate buckets in each sprint

## Slide 15: The Ugly
Take Agile Literature with a large grain of salt
  Always an idealized scrum
    One web eng., one DBA, 1 QA, etc.
  No one is a bottleneck
  Everyone can step in for everyone
  User Stories split easily
  Always fully self-sufficient
Agile in the real world is messy
  Bottlenecks in the scrum
  Dependencies on other scrums
  Customer support
  User Stories don’t break down easily
  Sometimes you need a real design . . .

## Slide 16: The Ugly
Good automation is critical for success . . . and no one tells you this explicitly
  Automation infrastructure becomes a bottle-neck
    Build environment/Rapid builds
    CI and Sanity testing
    Unit/Regression testing
    Test env. for each scrum
  Success in Agile requires significant investment in automation first year and beyond!
    Spent several person years here
    Improvements were well worth the effort
      Critical for waterfall too
      Don’t know how we managed until now

## Slide 17: The Ugly (con’t)
Self-empowered teams is a lofty goal
  Some engineers uncomfortable committing
  Some engineers just don’t care about Agile
  Critical mass of Agile enthusiast in the scrum is key
The tools (Jira) require customization
  Hard to reach agreement in global org
Need buy-in from other teams to succeed
  Tech Support – wants date for customer fixes
  Product Management – wants a 3 year roadmap
  Marketing needs a critical mass of features in a release

## Slide 18: The Ugly (continued)
Are we MORE efficient with Agile?!?
Short-term: No (decreased?)
  Felt efficient with waterfall
  Delivered fewer features
    Focused on infrastructure/CI/Automation
      From weekly build to every 4 hours
      From 2 hardening sprints to 1
      More stable and better automation
Medium-term: We think yes
  Just entering medium term now 
  More net development time (less hardening time)
  Better testing gives courage to make riskier changes
  Regressions get caught more quickly reducing wasted effort